KYAMBOGO                UNIVERSITY

FACULTY OF SOOCIAL SCIENCES

DEPARTMENT OF PSYCHOLOGY

COURSE UNIT: PROJECT PLANNING AND DEVELOPMENT

LECTURER’S NAME: DR METHODIUS TUMURANZYE

NAME: ADIKIN OLIVER

REG NO. 24/U/SSE/12731/PE

PROJECT TITLE: Enhancing Agricultural Productivity Through Modern Farming Practices

NAME OF ORGANISATION: MBALE FARMERS LEAGUE.

PROJECT LOCATION MBALE

DURATION OF PROJECT: ONE YEAR

DATE OF SUBMISSION: 19TH APRIL 2026

CONTACT/ EMAIL: 0781238095

EXECUTIVE SUMMARY

Agriculture remains the backbone of Uganda’s economy, employing a large portion f the population and contributing significantly to National food security and income generation.

In districts such as Mbale, agriculture is not only a source of livelihood but also a key driver of rural development.

Mbale district is known for its fertile soils and favorable climate which supports the cultivation of crops such as maize beans, coffee, bananas and vegetables. However, despite the potential, many farmers in the district continue to experience low productivity due to continued use of traditional farming methods.

Modern farming practices have the potential to transform Agriculture by increasing efficiency, improving yields and enhancing resilience to climate change. This project proposal aims to introduce and promote these practices among small scale farmers in Mbale district.

The project focusses on building farmers’ capacity improving access to input and promoting sustainable agricultural techniques. By doing so, it seeks to improve livelihoods, increase food production and contribute to economic development in the district.

By improving productivity, the project aims to enhance food security, increase household income and contribute to sustainable development in Mbale.

BACKGROUND AND CONTEXT

Mbale district s located in Eastern Uganda lies on the slopes of Mt Elgon. The district has fertile volcanic fertile soils and a favorable climate, making it suitable for a wide range of Agricultural activities. Major crops grown in the Area include maize, beans, coffee, bananas and vegetables.

However, despite these favorable conditions, agricultural productivity remains low. One of the main reasons is the high population pressure which has led to land fragmentation. Most farmers operate on small plots of land, making it difficult to practice large scale farming.

Another major challenge is soil degradation; continuous cultivation without proper soil management has led to nutrient depletion, resulting in reduced soil fertility. Many farmers do not use fertilizers or organic manure efficiently, which further worsens the situation.

Climate change has also had a significant impact on agriculture in Mbale. Unpredictable rainfall patterns, prolonged droughts and occasional floods disrupted farming activities and reduced crop yields.

In addition, access to agricultural extension services is limited. Many farmers lack the knowledge and skills needed to adopt modern farming practices such as irrigation, pest control, terracing, mulching and crop rotation. These challenges have contributed to low agricultural productivity, food insecurity, famine and poverty in the district or the region.

PROBLEM STATEMENT

Small scale farmers in Mbale district are facing persistent challenges that limits agricultural productivity. These challenges include reliance on traditional farming practices, limited access to improved agricultural inputs, lack of technical knowledge and ignorance especially among the youth who look at agriculture as a burden rather than a source of livelihood hence this becomes a problem in the district.

Most farmers use low quality seeds which produce low yields and are susceptible to pastes and diseases which may cause low productivity or poor yields leading to food insecurity. In addition, poor soil management practices have led to declined soil fertility further reducing productivity.

Furthermore, farmers have limited access to training and extension services. This prevents them from adapting modern farming techniques that could improve productivity since they do not have the knowledge and skills on how to use modern farming methods.

As a result, agricultural production remains low, affecting food security, household income and overall development in Mbale district and the region thus this becoming a crucial problem to the people living in the district.

JUSTIFICATION OF THE PROJECT

This project is justified because it addresses the critical issues affecting the livelihood of farmers in Mbale district improving agricultural productivity is essential for ensuring food security and reducing poverty.

The project aligns with Uganda’s national development strategies, which emphasize the modernization of agriculture. It also contributes to global development goals related to ending hunger and promoting sustainable agriculture.

By introducing modern farming practices, the project provides practical solutions to existing challenges. These practices have been proven to increase yields and improve efficiency.

In addition, the project focusses on capacity building, ensuring that farmers gain knowledge and skills that will enable them to continue improving their farming practices even after the project ends.

PROJECT GOAL

To enhance agricultural productivity and improve the livelihoods of small-scale farmers in Mbale district through the adaption of modern farming practices.

SPECIFIC OBJECTIVES

To train 200 farmers in modern farming practices within a period of 12 months.

To increase crop yields by at least 30% among participating farmers.

To improve access to quality agricultural inputs such as seeds and fertilizers.

To promote sustainable farming practices including soil conservation and irrigation.

To strengthen farmers’ knowledge and skills in modern agriculture.

TARGET BENEFICIARIES

The project will ensure gender inclusivity by involving both men and women. Youth will also be encouraged to participate, as they play  an important role in the future of agriculture.

The project will directly benefit 200 small-scale farmers in Mbale district. These farmers will be selected based on their willingness to participate and adopt modern practices.

Indirect beneficiaries will include the families of farmers, local markets and the wide community which will benefit from increased food production.

PROJECT ACTIVITIES

Community Mobilization

Community meeting will be conducted to create awareness about the project. Farmers will be informed about the benefits of modern farming practices and encouraged to participate.

Farmer Training

Training sessions will be organized to equip farmers with knowledge and skills in modern farming practices. Topics will include:

Proper land preparation

Use of proposed seeds

Soil fertility management.

Pest and diseases

Post-harvest handling.

Demonstration Farms

Demonstration farmers will be established to provide learning opportunities. Farmers will observe, practice and adopt modern farming techniques.

Distribution of inputs

Farmers will receive improved seeds, fertilizers, cultivators and basic tools to support implementation.

Extension of services

Agricultural experts will provide continuous support through regular field visits.

Implementation strategy

The project will use participatory approach involving farmers in all stages. This will promote ownership and sustainability.

Training will be practical and hands-on farmers will learn by doing, which increases understanding and adoption.

Partnerships with local authorities and agricultural officers will enhance implementation.

Expected Outputs

- 200 farmers trained

- Demonstration farms are established

- Agricultural inputs distributed

- Increased knowledge among farmers

Expect outcomes

- Increased agricultural productivity

- Improved household income

- Enhanced food security

- Adoption of modern farming practices

Monitoring and evaluation

Monitoring will be continuous throughout the project and data will be collected through

- Field visits

- Surveys

- Farmer interviews

Evaluation will be measured through

- Changes in crop yields

- Adoption rates of new/modern practices.

- Improvement of income levels

Risk analysis and mitigation

Risk1: Climate Change

Mitigation: Introduce irrigation and drought resistant crops

Risk2: Low Participation

Mitigation: strong community mobilization

Risk3: Limited resources

Mitigation Efficient budgeting and partnership

Sustainability plans

The project will ensure long term substantiality through

- Training farmers to become self-reliant

- Formation of farmer groups for knowledge sharing

- Linkages with extension services.

- Encouraging saving and re-investment

Budget

The budget will include training costs, for example facilitators and materials

Inputs such as seeds, cultivators and fertilizers among others,

Transport and logistics

Monitoring and evaluation

Administrative costs

Work plan

The project will be implemented over 12 months

- Month 1-2: mobilization and planning

- Month 3-6: training and input distribution

- Months 7-10: implementation and monitoring

- Months 11-12: Evaluation and reporting

Organizational Capacity

The implementation of organization has experience in community development and agriculture. It has qualified staff and access to necessary resources

Partnership and Stakeholders

- Mbale district local government

- Agricultural extension officers

- Community leaders

- Non-Governmental organizations (NGOs)

Conclusion

In conclusion, enhancing agricultural productivity in Mbale district through modern farming practices, presents a practical and sustainable solution to the persistent challenges of low yields, food security and rural poverty. The analysis clearly shows that traditional farming methods alone can no longer meet the growing demand for food and income in the face of climate variability, declining soil fertility and increasing population pressure. By introducing improved agricultural technologies, strengthening farmer knowledge and promoting efficient resource yields, this project offers a transformative pathway towards a more productive and resilient agricultural system.

The proposed intervention ranging from farmer training and demonstration plots to improve access to quality inputs and irrigation are not only relevant but also achievable within the local context.

These activities are designed to adopt modern practices effectively. Emphasizing inclusive participation particularly of women and youth ensures that the benefits of the project are widely shared and contribute to social as well as economic development

Furthermore, strengthening farmer groups and market linkages will help sustain productivity gains beyond the project period by improving access to markets, financial services and collective action.

Importantly, the longtime impact of this project extends beyond immediate increase in crop yields. It will contribute to improved household incomes, enhance food security and greater resilience to climate related shock. As farmers adopt climate-smart and sustainable practices, the project will also support environmental conservation particularly through better soil management and efficient water use. With proper monitoring and continued support from stakeholders, the outcomes of this initiative can be scaled up or replicated in other regions facing similar challenges.

Overall, this project presents a strategic investment I the agricultural sector of Mbale district. By addressing key productivity constraints and promoting innovation, it lays a strong foundation for sustainable rural development. The success of this initiative will depend on effective implementation, stakeholder collaboration and the commitment of farmers to embrace change. If well executed, the project the potential to significantly improve livelihoods and contribute to broader national development goals in Uganda.

ANNEXES / APPENDICES

APPENDIX 1: CURRICULUM VITAE (CVs)

1.1 Project Coordinator – Mr. John Wanyama

Professional Profile:

Experienced agricultural specialist with 10+ years in rural development, extension services, and project coordination.

Education:

- MSc Agricultural Extension – Makerere University

- Bachelor of Agriculture – Busitema University

Experience:

- Project Officer (2018–Present)

- Extension Worker (2012–2018)

Skills:

Project management, climate-smart agriculture, M&E, farmer training.

1.2 Agricultural Extension Officer – Ms. Sarah Namatovu

Profile:

Expert in sustainable agriculture and farmer training.

Education:

- BSc Agriculture – Kyambogo University

Experience:

- Extension Officer (2016–Present)

Skills:

Soil management, pest control, community mobilization.

1.3 Finance Officer – Mr. David Okello

Profile:

8+ years in NGO financial management.

Education:

- Bachelor of Commerce (Accounting)

Skills:

Budgeting, reporting, audit compliance.

APPENDIX 2: LETTERS OF SUPPORT

Mbale District Local Government:

Supports project implementation, provides extension services, and mobilizes farmers.

Farmer Cooperative:

Commits to participation and adoption of modern practices.

Partner NGO:

Provides technical support and training.

APPENDIX 3: MAPS

Project Area:

Mbale District, Eastern Uganda.

Coverage:

Bungokho, Bubyangu, Wanale.

APPENDIX 4: DATA TABLES

Baseline Yield:

Maize: 1.5 → 3.5 tons/ha

Beans: 0.8 → 2.0 tons/ha

Coffee: 0.5 → 1.2 tons/ha

Beneficiaries:

Farmers: 1000

Women: 600

Youth: 300

Budget Total: $130,000

APPENDIX 5: WORK PLAN

Month 1: Baseline

Months 2–6: Training

Months 3–6: Input distribution

Month 12: Evaluation

APPENDIX 6: SUPPORTING EVIDENCE

Photos, demonstrations, farm meetings.

APPENDIX 7: RISK ANALYSIS

Climate risk → irrigation

Low adoption → training

Pests → pest management